}

Guide 1. APT Project Definition

Capstone Course

- PART I

1. Personal Information

The following table must be completed with the requested information.

| Student name | - Jesús Ferrari - Emilia Guajardo - Benjamin Muñoz - Ariel Salinas |
| --- | --- |
| RUT | - 19.729.320-9 - 21.735.878-7 - 18.451.498-2 - 21.585.915-0 |
| Program | Computer Science Engineering |
| Campus | Puente Alto |

2. APT Project Description

In the description, briefly state the name of your APT project and the graduation profile competencies that you will put into practice. If your program defines performance areas, also mention which areas of performance the project is related to.

| Project name | Redsol Service |
| --- | --- |
| Performance area(s) | Software and mobile application development; database design and management; requirements engineering; IT project management; software quality. |
| Competencies | Design and create innovative, high-quality software solutions by applying their life cycle and good practices. Design solutions for information requirements through databases. Design and adapt requirements engineering processes. Evaluate and manage projects using traditional and agile methodologies. Design software with a focus on quality, security and sustainability. Develop projects for mobile platforms and devices. |

3. APT Project Rationale

The following fields must be completed with the requested information. This section aims for you to describe your project in detail and justify its relevance and suitability.

| Relevance of the APT Project | In Ciudad del Sol, in the commune of Puente Alto, residents look for plumbing, electrical, gardening and other trade services through recommendations and scattered posts. This makes it difficult to compare alternatives, check background information and follow up on requests. Service providers also need an organized channel to promote their work. Redsol Service seeks to centralize this information and facilitate contact, hiring and service evaluation. I chose this project because it allows software engineering and data management to be applied to a specific community need. Its professional contribution consists of integrating requirements, applications, data and quality controls into a useful technological solution. |
| --- | --- |
| APT Project Description | The project consists of developing a mobile application for residents and service providers, an administrative website, a REST API and a MySQL database. It will allow users to register, publish and search for services, manage requests, agree on amounts, check statuses, rate completed work and receive notifications. Payments will be integrated through Mercado Pago Checkout Pro. The website will allow users, roles, categories, neighborhoods and other data to be managed, as well as generate reports exportable to PDF and XLSX. The solution will use layered architecture and role-based access control. My main responsibility will be to design and implement the database and integrate it with the backend. |
| Alignment of the project with the graduation profile | The project applies software development competencies through the mobile application, the website and its API. Requirements engineering will make it possible to define functions, business rules and acceptance criteria. Project management will be reflected in planning, assigning responsibilities and tracking sprints. In my role, I will especially apply the competency related to information solutions: I will design the relational model, constraints, queries and MySQL backups. Quality and security competencies will be used to validate data, control permissions and test integrations. These skills are necessary to maintain consistent information and verify that the solution responds to user needs. |
| Relationship with professional interests | My professional interests are related to data analysis, business intelligence, Big Data, cloud technologies and project management. Redsol Service will allow me to work with information about users, services, requests and evaluations, designing a database that can support queries, reports and indicators. My role as database administrator is directly connected to those areas. I will also be able to strengthen my skills in Python, platform integration and collaborative work. Although the project is centered on a service application, its data and reporting component will contribute to my professional development and help improve programming competencies that I need to reinforce. |
| Feasibility of developing the APT Project | The project is planned for the period from August 12 to December 2, 2026, with a team of four students and defined responsibilities. Computers, internet access, Git, development tools, MySQL and a testing environment are required. The work must be organized according to the actual hours available for the course and for the team, avoiding the assumption of full-time dedication. Prior knowledge, available tools and instructor feedback will facilitate its development. The main risks are broad scope, delays and integration difficulties. The proposal is to prioritize mandatory requirements, review progress weekly, perform early integration testing and use the payment testing environment. If there are not enough users available for validation, early sessions will be coordinated and the limitations will be documented. The complete development target will be November 11, according to the milestone stated in the project charter. It is proposed to move the development end date ahead of November 13, which is indicated in the SRS and roadmap, and to coordinate this adjustment with the team. |

- PART II

4. Objectives

In this section, you must define the general and specific objectives of the APT Project. It is important to state the objectives clearly and concisely, without additional explanations, so that they can be understood on their own. It is recommended to write them using an infinitive verb, as this helps specify concrete actions.

| General objective | Develop Redsol Service, a mobile and web solution that centralizes the offering, request, tracking and evaluation of trade services in Ciudad del Sol, through a REST API and a relational database, during the academic period from August to December 2026. |
| --- | --- |
| Specific objectives | 1. Define the functional requirements, non-functional requirements and business rules of the solution. 2. Design the layered architecture, interfaces and MySQL relational model. 3. Implement the mobile application, the administrative website and the REST API with the mandatory requirements, ten maintenance modules and at least two reports exportable to PDF and XLSX. 4. Integrate role-based authentication, notifications and payments through Mercado Pago Checkout Pro. 5. Validate 100% of the critical requirements and pass at least 95% of the acceptance test cases, with no open critical defects. 6. Deliver the system, database script and closing documentation no later than December 2, 2026. |

5. Methodology

In the following section, you must describe the methodology from your discipline that you will use to address the APT project described above, including the stages and work methods.

Description of the Methodology

An agile methodology based on Scrum will be used, organized into sprints and incremental deliveries. The proposal is to work with two-week sprints and weekly coordination, adjusted to the academic milestones. Each cycle will include selecting backlog tasks, assigning responsibilities, development, testing and review of the increment. Difficulties and scope changes will be recorded in order to agree on adjustments with the project manager. The process includes requirements gathering and validation, interface and data design, construction and integration, testing, implementation and closure. Acceptance criteria will guide the review of each functionality. Git will make it possible to maintain shared versions of the code, while the work board will facilitate task tracking. Emilia Guajardo: planning, coordination, monitoring and interface design. Ariel Salinas: analysis and programming of the application, website and API. Benjamín Muñoz: data model, MySQL implementation, queries, integrity and backups. Jesús Ferrari: test design and execution, defect logging and quality verification. The team will participate in reviews and integration testing. It is proposed to apply the threshold from the project charter for final acceptance: 100% of critical tests and at least 95% of the total tests passed. This criterion must be unified with the documentation sections that mention 90%.

6. Evidence

Next, describe which evidence will be evaluated in the progress report and in the final report of your APT project. This evidence must be agreed upon with your instructor. Evidence refers to the products developed during the project whose purpose is to show or document how the work has been implemented.

| Type of evidence (progress or final) | Evidence name | Description | Justification |
| --- | --- | --- | --- |
| Progress | Requirements and use cases | SRS, requirements spreadsheet and completed use cases. | They make it possible to verify the coverage of needs, actors and business rules. |
| Progress | Architecture and prototypes | Component design, mockups and relational model. | They show how the solution will be organized before implementation. |
| Progress | Planning and sprints | Gantt chart, WBS, backlog and progress reports. | They connect tasks, people responsible and deadlines; they document progress and difficulties. |
| Final | System and integration | Application, administrative website, API and code repository. | They make it possible to demonstrate the operation of the requirements through testing and a demo. |

7. Work Plan

In the following table, define the planning of your APT Project according to the requirements.

| APT Project Work Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Competency | Activity/Task | Task Description | Resources | Duration | Responsible | Observations |
| Project management | Plan | Define scope, roles, WBS and costs. | Team; charter; Gantt chart. | Aug. 12-18 | Emilia and team | Facilitator: defined roles. Risk: overload; review availability. |
| Requirements and design | Analyze and design | Complete requirements, use cases, mockups and data model. | SRS; UML editor; MySQL. | Aug. 19-Sep. 4 | Team according to role | Risk: ambiguous requirements; validate acceptance criteria. |
| Databases and software | Build and integrate | Implement MySQL, application, website, API and payments. | Python; Django; MySQL; Git. | Sep. 7-Nov. 11 | Ariel and Benjamín; team support | Risk: integration; test modules from the first sprints. |
| Software quality | Test and correct | Run tests, log defects and validate with users. | Testing environment; cases and records. | Nov. 12-25; testing by sprint | Jesús and team | Risk: low user availability; coordinate sessions. |
| Management and quality | Implement and close | Prepare deployment, backup, manuals and delivery. | Server; repository; documentation. | Nov. 26-Dec. 2 | Emilia and team | Risk: final defects; review acceptance before delivery. |

8. Gantt Chart

Choose a Gantt chart format that works for you and use it to organize the activities planned in the previous section, considering the period assigned for the development of your APT Project. You must keep the timing of the academic period across the three phases included in the Degree Portfolio course.

| Activity | Phase 1 |  |  |  | Phase 2 |  |  |  |  |  |  |  |  |  |  |  | Phase 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | W 1 | W 2 | W 3 | W 4 | W 5 | W 6 | W 7 | W 8 | W 9 | W 10 | W 11 | W 12 | W 13 | W 14 | W 15 | W 16 |  | W 17 | W 18 |
| Plan | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Req. |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Dev |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |
| Tests |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |  |
| Close |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |
| End |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |

If the APT Project is developed as a group project, this column must indicate the names of the people responsible for each task or activity. This will later make it possible to differentiate the evaluation for each team member.